# The MobilePoint Development Process

Fred Braddock

Revision 0 4/10/98

DRAFT

# Documents Involved

## Purpose of this document

The purpose of this document is to lay out the development process that we should plan to follow for MobilePoint development.  I have placed emphasis of defining the documents so that we all understand what these are intended to achieve and the parts that we all play.  In this edition, I have also included my observations on where we are.

This is more of an overview than a completely definitive cradle to grave definition.  This document will evolve with the view of becoming a document to which all MobilePoint employees have access.

For the purposes of this document I have focussed on the development activities i.e. the process of building (or coding).

There are two development activities within MobilePoint; System Development (e-case and HQ server – done at San Jose) and Application Development (Tablet app and customization – done at El Segundo).  While the tools used for each development activity differ, the process for both is a software development process.  All of the items in this document apply equally to the activities in San Jose and El Segundo

There are many other functions involved in producing a product, not least of which are QA and Documentation.  However, for the moment, I want to focus on the framework for the coding/scripting development process itself.

## Terminology

I have used terminology that is reasonably common throughout the industry.  However, I note that Clairol has a variant terminology and so it is important when communicating with people outside of MobilePoint that you establish that they understand your terminology (or you understand theirs)

## The Documents

In our development process we should focus on generating the following documents:

- Requirements Document (which identifies the business requirement i.e. WHAT is wanted)

- Functional Specifications (which describe the look and feel and operational features of what is to be built)

- Design Specification (which describes the nitty gritty details of HOW this is going to be built)

- Project Plan (which outlines the steps which are necessary to build the product)

- Internal Documentation (which describes what was actually built and how it comes together)

- User Documentation ( which is given to the user so that he knows how to use that which was built)

## Requirements Document

This states what the buyer wants to have built.  It is a high level document that focuses on the business requirements.  It is the buyer’s responsibility to produce this.  This document is normally not more than two pages long and can be as short as a paragraph.

This is a document that the president of the company would understand.  In the case of Clairol Aps we should be able to show this document to any salon operator and they would understand it.  It just states what is required – not how it is to be done.  That comes later.

Example:

Requirement: I want a vehicle that will transport 18 people and a horse and a pig.  I will also want to prepare meals.  Sleeping accommodation is not required.

## Functional Specification

This document responds to the requirements.  It basically says “In response to the requirement, this is what we will provide….”  NOTE – not how we will do this, just what we will do.

This document outlines what the thing that was requested will look like,  It describes the functions (things) that can be done and what to do to make them happen.  It takes the abstract requirement and turns it into a concrete reality.  It outlines how it can be used, calling sequences, look and feel etc.  It goes into the level of describing how it will react upon usage  -- i.e. if you tap this you will get that.

It tells the buyer what he will get in response to his requirement.

The person that generates this step is normally a designer.

Each reader has their own independent vision of the vehicle that will satisfy the requirements that I stated above.  Some will see it as a bus partitioned somehow, some will see it as a minibus with a U-Haul trailer attached, others will see it as a Winnebago with an extension.  Given that there is no agreement as to what will be built, it is clearly unacceptable to let anyone go and build anything.  As buyer, I want to know what I am getting.  In this illustration, I would like to have a drawing of the external appearance, a layout of the internal space allocation and a cut away that shows how it is all arranged.  Only when I am happy with what I am going to get would I commission any building.  This process requires review and iteration because my family also have opinions.

It is important that we know ahead of time what we are going to build.  It is far harder and more costly to fix something after the fact.  In some cases it is not possible and this results in a poorer product.

Consider if I do not get a functional spec.  You build my vehicle and proudly deliver it to me.  I take one look at it and say “What do you mean that you put the pig partition behind the driver?  Do you realize what that will smell like on a long journey?  You have to fix this and I need the vehicle on Monday”  You have no time to fix things properly.  The cost of a major redesign is prohibitive.  You resort to adding a fan to the pig partition to try to divert the smell.  In other words, a pathetic response to a problem that should not have happened if the spec. had been created and reviewed.

I didn’t get what I wanted.  The product is inferior.  This is what happens when you don’t create a functional spec up front and review it.

As implied in the illustration above, this step requires several cycles of peer review.  If we think it through and get everyone’s input, building it won’t be a problem.

It is at the Functional spec stage that we can take a first estimate at the cost.  I don’t want you to build my vehicle until I have some handle on what it will cost.  Unfortunately, at this stage all we have are pictures and documents.  However, an experienced individual who has trod similar paths before can make a guess based on experience.  The reason that none of us can estimate my vehicle requirement is that we have no experience in building vehicles – we are way out of our depth.  However, in our field of MobilePoint development, we have experience.  I would expect Clay to be able to estimate for engineering, Nancy to estimate for PSG and Laynee for TSG.  Granted that the estimates would be better with more time and study and granted that there are others who may be able to give somewhat better estimates – but the fact is that when you have the responsibility for an area, you have to be able to speak for it.  It comes with the territory.

While scoping is required, it also has to be acknowledged that at this stage we are dealing with intelligent guesswork.  When the details are known, the story may be entirely different.  That’s why so many government and defense contracts end up costing much more than the original estimate.

## Design Specification

Now we get down to the details.  These are the detailed instructions on how to build the item.  For my vehicle it is blueprints, architectural documents, bill of materials, dimensions, parts etc.  When this design specification document (or most likely several documents as the project is broken into manageable parts) is complete it should be able to be farmed out to people who will follow the instructions and build the item.  Note that if this job is done properly, the building process should be routine and that which is build will be that which is expected.

The individual who performs this step is an architect.

This is also a step that requires peer review.

This step is important because it means that once done, anybody can build (or rebuild) the thing.  It also preserves continuity in the event that half way through the building process there has to be a change in personnel that there will be very little impact.  The issue of how to complete the task in the event of the loss of staff, is something that each manager must worry about.

It is after this step that we can make estimates and build a project plan in which we have some degree of confidence.

## Project Plan

This outlines the steps and sequence of events that must occur to complete the task.  Given that we are still guessing at the future and that the future is always full of unkowns, the estimates used should contain some contingency to allow for these.

## Internal Documentation

If we have done our job right, this will be an update of the design specifications.  In the course of development, there will be changes (hopefully minor) to account for unforeseen problems or changes to the requirements (hopefully controlled).  But taking the design documents and updating them should leave us with documentation which reflects the internals of what was built.

## User Documentation

This is the documentation that is turned over to the user.  It should be based heavily on the Functional specification.  It will generally reorganize the material, provide more examples and contain extra tutorial material.

# Other Considerations

## Many Hats

The above description shows that many people are involved in the product building process:

- Designer

- Architect

- Builder (programmer)

In larger companies these are separate and distinct people (groups).  In a company like MobilePoint, the functions are frequently performed by the same individual.  But do not lose sight of the fact that that individual is performing different functions.  Just because there is only one person, doesn’t make the function go away.  In a startup company people wear many hats.

# Mobilepoint and where it stands

It is worth stating that in the real world no company ever achieves a perfect development process (at least I’ve never seen one).  But the good companies are close and when they violate the process they generally know that they are doing so and do so for a reason not simply as the result of not knowing or neglecting the process.

Further, I do not expect that we can correct all issues overnight.  But if we understand where we are we can work towards shoring up the weaknesses.

Given the above, here are some of my observations on MobilePoint development.

### e-case and HQ server

- Requirements Document

These are being produced and identify the requirements for the current projects.

Functional Specifications

These are being produced for all major components.

Design Specification

I have not seen any of these.  This is probably the weakest area of development at the current time.  There is an informal design review process because the group is small and, at the moment, informal interaction substitutes for review.

Project Plan

These are produced and used. (The TSG organization also has a very detailed plan).

Internal Documentation

Much of the product is inherited and lacks documentation.  There is an active effort to create the documentation as resources and time is available.

User Documentation

This is created.

### Application Level

I have spent less time in this area and so these comments are subject to revision:

- Requirements Document

- Don’t exist.  Currently under development

Functional Specifications

- Don’t exist (the current Clairol 1.1 functional spec is really “internal documentation” – see below.

- Design Specification

No methodology

Project Plan

I have not seen a MobilePoint plan.  There is not a MobilePoint created plan that specifically addresses Clairol 1.1 and its development.  The only plan is embedded within Clairol plans and is not under the direct control of MobilePoint.  The TSG organization has a very detailed plan covering the testing and release process.

- Internal Documentation

There is a document published as a functional spec which is closer to a set of release notes with some design notes.

- User Documentation

This is created