## Developing ISAs

Developing ISAs on the electronic briefcase has the same basic software engineering phases that all sound projects must have: Definition, Requirements, Design, Implementation, Test, Release, and Maintenance.  A Methodology defines the processes and components of each phase and the criteria for going from one phase to the next.

### The JAM Methodology

The Methodology for ISA development will be more thoroughly defined in the next few months.  The methodology called JAM (Joint Application Modeling) is very closely related to JAD (see "Joint Application Development" by Jane Wood/Denise Silver), except more emphasis is on using our toolkit pieces for modeling in the early phases of development.  The key tool of the Definition phase is proof-of-concept modeling.  The Requirements phase relies significantly on rapid prototyping.

Our technology allows end-user experts to develop and demonstrate functions quickly, in fact while they are with the actual end-users themselves.  Expressing, understanding and eventually "buying into" the project is the strength of these processes melded with our technology.  The JAM methodology  enlists end-users to play significant roles in the modeling during “sessions”.

Besides JAD, the JAM methodology is based on experience of our previous customer implementations, key differentiation of our technology, the profiles of end-user expert developers, and the Sales Cycle as suggested by MobilePoint Sales.

The JAM development methodology for creating an ISA is outlined below.

| Phase | Step | Work Days |
| --- | --- | --- |
| Definition | Needs Analysis - Evaluation Session I - Follow-up interviews/research Prepare Project Definition - Management Project Definition Guide - Proof-of-concept Evaluation Session II Present Project Definition Define Project Team & Schedule JAM Session (s) | 1 to 3 days 2 to 4 days 1 day 1 day |
| Requirements | Begin prototype, modeling business processes and data requirements Prepare functional specification JAM Session(s) Prepare requirements presentation Present Functional Specification & Prototype | 3 to 5 days 2 to 3 days 1 to 3 days 2 to 3 days 1 day |
| Design | Implementation Plan Define data model and document processes. | 2 to 3 days 3 to 10 days |
| Implementation | Develop ISA | 10 to 30 days |
| Test | Pilot Phase I Pilot Phase II | 30 to 40 days 30 to 40 days |
| Release | Full rollout begins |  |

### Maestro

Key to the success of the JAM phases is the role of the Maestro.  A Maestro is an expert  in sales processes and technically  trained and certified as a developer on the electronic briefcase solution framework.  The Maestro is both chief analyst and chief developer.  The facilitates the JAM sessions. There is only one Maestro, and this key project team member must be involved from the Definition to Release phases.

Modeling is key to success and rapid development.  The Maestro is a master modeler and uses modeling for effective communication during the definition and requirements phases.