# Life Cycle Documentation

## Fred Braddock

3/1/98

Revision 0

Approved By: ____________________

Date: ____________________

File: input.doc

## Summary of Revisions

Revision 0	First edition.

# Life Cycle Documentation

The following describes the steps and the documentation required in the product life cycle.

## Step 1: Requirements Document/Marketing Requirements Document (MRD)

This document is the first document created.   It is normally brief and to the point.  The document describes What is to be done, and if possible, why this is wanted.  The purpose of the document is to ensure that MobilePoint and the customer agree on the scope of the work.  It is important since what is ultimately delivered should be no more and no less that that which satisfies the requirements.

The document is necessary as, almost without fail, during the development or upon delivery the customer will expect something not agreed to.  The Requirements Document is MobilePoint’s defense.

### Caveats

1) This can be a difficult document to write since very frequently the customer (and MobilePoint personnel) will state requirements in terms of a solution.  This is a trap and should be avoided.

Example:

Poor Requirement:  There shall be a delete button.

Good Requirement:  Capability to delete items shall be provided.

2) Dates have no place in a Requirements document.  It a date is a requirement, it is almost certainly a recipe for failure.

## Step 1a: Scoping

This provides a high level cut at the cost and time involved.

This step should be avoided if at all possible since it is only inspired guesswork.  The step is included here because often it is inevitable that the customer will want to have an overall feeling for the cost or time of the project.

Regrettably, the initial scoping will be set in concrete and become a millstone around MobilePoint’s neck.  It must be continually emphasized that this is a wild guess and MobilePoint is not committed to these times or numbers.

## Step 2: Functional Specifications.

This document identifies how the requirements will be satisfied at the customer level.  The document is quite extensive and should function as Draft 1 of the User manual.  It is generally a thick document and takes time to develop.  Coding should never begin until this document exists.  If we don’t know what it looks like, we should not attempt to build it.

## Step 2a: Project Estimate.

It is only when the Functional spec exists that the project can be properly estimated.  Even this is an estimate.  Just as an auto mechanic guesses at what it will cost to repair your car and will actually charge something different (and will inform you of a significant change of scope in additional work), so it must be expected that the Project estimate is the best attempt at understanding what it will take.

## Step 3: Design Documents

These are technical in nature and internal to MobilePoint.  These state, in detail, how the functional specifications are going to be materialized.