Wander Status

- Operations & Business Plan

  - Presentation

    - Introduction (5-min)

      - draft completed

      - complete slides & videotape it july 6

    - User Features/Demo

      - draft completed

      - complete slides & videotape it july 6

    - Executive Overview

      - draft completed

      - complete slides & videotape it july 6

    - Sales & Market Plan

      - strawman July 6

    - Technology Plan

      - strawman July 6

    - Finance Plan

      - strawman July 6

  - Business Plan

    - Draft by July 6 – except for 4,5 & 6 above

  - Meet with score – Mid july

- Lucent/Penpoint licensing:

  - Ramsey says brass has approved.  Lucent going through turmoil…status on hold.

  - Need to determine negotiation position

  - Can wait.

- Ricochet Reselling

  - WWC meeting create promising picture for reselling as independent representative.

  - Call Debra ****

- Homeworks Reseller

  - On hold, waiting for demo machine to be returned.

  - Set up meeting with REI or C21 first?  Identify middleman….

- Fujitsu Reseller

  - Luna has iVar program and is interested in supporting us.

    - received contract/cost sheet estimated now (new model out 3500)

    - Kelly likes the 500SL

  - Located in downtown Campbell

- Operations/Finance Plan

  - first and second year cost/profit review

  - compare with everdream model

  - meet with score on bus model

- Product Marketing Plan

  - Wanderbook  I near completion/need more feedback

    - clay to write up

    - need to evaluate/figure out

      - “top producer” software

      - prompt & response mls

      - note taking software

      - handrecognition

      - true pen

      - ms office

      - printing & local area networking

  - Have sales literature prepared

  - Wanderbook II draft 50% complete – long term

- Legal & Admin

  - Capitalization

  - Inform Steve

  - CPA (tax…)

  - Open a bank account for the business

  - Have business cards and stationery printed patent

- InCorporation

  - Capitalization  Clay/Therese/Others…

- Pilot program

  - Kelly – received fuji back late last week. One more week trial

  - Need feedback from c21 top producers

  - Therese - Need to telephone interview leads gained last month

    - survey should obtain onfo for

      - pricing

      - features

      - value

- web site? Get an email address

  - on hold

- location for the business

  - Weimer house (100 sq ft home based tax advant.)

  - Check Campbell zoning laws, required business licenses or permits ($<50)

  - Order any required notices (advertisements you have to place) of intent to do business